## Summary
Project ID |  |  |  |  | Planned Start |  | 2024-02-23 |  |  |  | Estimated Test case Effort(Hr) | 4 | Testing Type | Internal Testing |  | STATUS
Project Name |  | Asset Management System |  |  | Planned End |  | 2024-02-25 |  |  |  | Estimated Testing Effort(Hr) | 4 | Testing Method | Manual | Manual (Onsite)
Project Manager/Lead |  | Nilesh Kumar |  |  | Actual Start |  | 2024-02-29 |  |  |  | Actual Test case Effort(Hr) | 4 | TEST Data Status | Available |  | Recommended for Delivery(OK)
Project PIC | Sourabh | Surbhi |  |  | Actual End |  | 2024-03-01 |  |  |  | Actual Testing Effort(Hr) | 4 | Test Round | 2
Test Manager |  |  |  |  | TCN |  | 159 |  |  |  | Defect Density | 0 | Sonar Status(Quality)
Test PIC | Sourabh |  |  |  | TCN Pass (%) |  | 100% | [5 empty] | Line of Codes
Testing Round |  | Actual |  |  | Test Cases |  | TCN Status
Sno | Tester | Start Date | End Date | Effort(Hrs) | No of Test Case Notes |  | Pass | Fail | Not Run | On Hold | Blocker | Pass with Exception | Testing Confirmed By | Testing Status |  | Scope
1 | Abhinandan Kumar | 2024-02-29 | 2024-02-29 | 4 | 145 |  | 141 | 4 | 0 | 0 | 0 | 0 |  | Not Recommeded for Delivery(NG)
2 | Abhinandan Kumar | 2024-03-01 | 2024-03-01 | 3 | 145 |  | 145 | 0 | 0 | 0 | 0 | 0 |  | Recommended for Delivery(OK)
3 | Abhinandan Kumar | 2024-03-07 | 2024-03-07 | 4 | 159 | 1900-03-01 | 2 | 0 | 0 | 0 | 0 | 0 |  | Not Recommeded for Delivery(NG)
4 | Abhinandan Kumar | 2024-03-11 | 2024-03-11 | 4 | 159 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Recommended for Delivery(OK)
Test Case Review History
Version | Prepared By | Change Description | Reviewed By | Reviewed On
Version0.0Draft-1 | Abhinandan Kumar | Initial draft | Surbhi | 2024-03-04
Version0.0Draft-2 | Abhinandan Kumar | New test cases incorporated

## Test Cases >>
Testing Round Summary

## Test cases
Sr No | Use Case Id | Type | Priority | Test Case | Verification Method | Expected Results | Test Data | X | Round 1 Status | Bug Id | X | Round 2 Status | Bug Id | Round 3 Status | Bug Id
1 | NA | Functional | High | Check when Server is start. | Visual | Database connection should be successful. |  |  | Pass |  |  | Pass
2 | UC-001: Login | User Interface | Low | Check when 'Login Screen' is Executed. | Visual | Screen Layout should be proper. |  |  | Pass |  |  | Pass
3 | UC-001: Login | User Interface | High | Verify Content Display when 'Login Screen' is executed. | Visual | Login Form should be displayed |  |  | Pass |  |  | Pass
4 | UC-001: Login | User Interface | Medium | Verify Position and Alignment of Buttons in login form. | Visual | Login button should be positioned below the input fields. |  |  | Pass |  |  | Pass
5 | UC-001: Login | User Interface | High | Verify Editability of Email, and Password Input Fields in login Form. | Event - Click | The email and password fields should be editable. |  |  | Pass |  |  | Pass
6 | UC-001: Login | User Interface | High | Verify clickability of login Button in Register Form. | Event - Click | Login Button should be clickable and active by default. |  |  | Pass |  |  | Pass
7 | UC-001: Login | Validation | High | Check when email is passed empty and login button is clicked | Test Data | Error message "Please fill this field" should be displayed. | TD01 |  | Pass |  |  | Pass
8 | UC-001: Login | Validation | High | Check when password is passed empty and login button is clicked. | Test Data | Error message "Please fill this field" should be displayed. | TD02 |  | Pass |  |  | Pass
9 | UC-001: Login | Validation | High | Check when invalid email format is passed and login button is clicked. | Test Data | Error message "Invalid email format" should be displayed. | TD03 |  | Pass |  |  | Pass
10 | UC-001: Login | Validation | High | Check when invalid password is passed and login button is clicked. | Test Data | Toast error message 'Password should be at least 8 characters long,' should be displayed | TD04 |  | Pass |  |  | Pass
11 | UC-001: Login | Functional | High | Check when user clicks on text 'Log In' and all fields are filled with valid inputs | Test Data | User should successfully redirect to the portal page depending on the user role. | TD05 |  | Pass |  |  | Pass
12 | UC-001: Login | User Interface | High | Check when user is successfully loggedin when user_role is admin | Visual | User should successfully redirect to the admin portal page. |  |  | Pass |  |  | Pass
13 | UC-001:Login | User Interface | High | Check when user is successfully loggedin when user is employee | Visual | User should be redirected to the employee portal page. |  |  | Pass |  |  | Pass
14 | UC-002: Admin Portal | User Interface | High | Check when Admin Portal Screen is executed. | Visual | Admin Portal Screen should be displayed. |  |  | Pass |  |  | Pass
15 | UC-002: Admin Portal | User Interface | High | Verif Content Display when 'Admin Portal Screen' is executed. | Visual | Admin Portal screen should display cards with headings as Budget Data and Assets Count. Screen should have a bell and hamburger icon in the navbar. |  |  | Pass |  |  | Pass
16 | UC-002: Admin Portal | User Interface | Medium | Verify Position and Alignment of Button in admin portal screen. | Visual | All buttons should be positioned in the navbar and in the side bar |  |  | Pass |  |  | Pass
17 | UC-002: Admin Portal | User Interface | Medium | Verify Position and Alignment of admin portal cards. | Visual | In the Admin portal, under the Budget Data heading there should be three cards and under Assets Count heading there should be twelve cards |  |  | Pass |  |  | Pass
18 | UC-002: Admin Portal | User Interface | High | Check if cards of admin portal screen is clickable | Event - Click | Cards should be clickable |  |  | Pass |  |  | Pass
19 | UC-002: Admin Portal | Functional | High | Check when click on cards under budget data header on admin portal screen. | Event - Click | Update budget modal should be displayed. |  |  | Pass |  |  | Pass
20 | UC-002: Admin Portal | User Interface | High | Check when click on total assets cards under Status Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Assets Data header |  |  | Pass |  |  | Pass
21 | UC-002: Admin Portal | User Interface | High | Check when click on allocated assets cards under Status Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Allocated Assets header and table should display data of allocated assets |  |  | Pass |  |  | Pass
22 | UC-002: Admin Portal | User Interface | High | Check when click on unallocated assets cards under Status Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Unallocated Assets header and table should display data of unallocated assets |  |  | Pass |  |  | Pass
23 | UC-002: Admin Portal | User Interface | High | Check when click on total laptop assets cards under Category Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with laptop Assets header and table should display data of laptop assets |  |  | Pass |  |  | Pass
24 | UC-002: Admin Portal | User Interface | High | Check when click on total desktop assets cards under Category Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with desktop Assets header and table should display data of desktop assets |  |  | Pass |  |  | Pass
25 | UC-002: Admin Portal | User Interface | High | Check when click on total dongle assets cards under Category Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with dongle Assets header and table should display data of dongle assets |  |  | Pass |  |  | Pass
26 | UC-002: Admin Portal | User Interface | High | Check when click on total mobile assets cards under Category Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with mobile Assets header and table should display data of mobile assets |  |  | Pass |  |  | Pass
27 | UC-002: Admin Portal | User Interface | High | Check when click on total YNA assets cards under Team Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Total YNA Assets header and table should display data of assets llocated to YNA team employees |  |  | Pass |  |  | Pass
28 | UC-002: Admin Portal | User Interface | High | Check when click on total OSS assets cards under Team Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Total OSS Assets header and table should display data of assets llocated to OSS team employees |  |  | Pass |  |  | Pass
29 | UC-002: Admin Portal | User Interface | High | Check when click on total SAP assets cards under Team Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Total SAP Assets header and table should display data of assets llocated to SAP team employees |  |  | Pass |  |  | Pass
30 | UC-002: Admin Portal | User Interface | High | Check when click on total ETI assets cards under Team Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Total ETI Assets header and table should display data of assets llocated to ETI team employees |  |  | Pass |  |  | Pass
31 | UC-002: Admin Portal | User Interface | High | Check when click on total Microsoft assets cards under Team Wise sub header on admin portal screen | Visual | User should be redirected to Assets Details screen with Total Microsoft Assets header and table should display data of assets llocated to Microsoft team employees |  |  | Pass |  |  | Pass
32 | UC-002: Admin Portal | User Interface | High | Check when click on add budget button in the navbar | Event - Click | Add budget modal should be displayed. |  |  | Pass |  |  | Pass
33 | UC-002: Admin Portal | User Interface | High | Check when click on Register New Asset button in the navbar | Event - Click | Register new asset modal should be displayed. |  |  | Pass |  |  | Pass
34 | UC-002: Admin Portal | Functional | High | Check when click on the hamburger button in the navbar | Event - Click | Sidebar should be displayed. |  |  | Pass |  |  | Pass
35 | UC-002: Admin Portal | User Interface | High | Check when side nav bar is displayed | Visual | Track Issues, Add user and Add vendor button should be displayed in the side navbar. |  |  | Pass |  |  | Pass
36 | UC-002: Admin Portal | User Interface | High | Check when click on the Track Issues button in the side navbar | Event - Click | User should be redirected to the Track Issues screen. |  |  | Pass |  |  | Pass
37 | UC-002: Admin Portal | User Interface | High | Check when click on the Add Vendor button in the side navbar | Event - Click | User should be redirected to the Add Vendor screen. |  |  | Pass |  |  | Pass
38 | UC-002: Admin Portal | User Interface | High | Check when click on the Add User button in the side navbar | Event - Click | User should be redirected to the Add User screen. |  |  | Pass |  |  | Pass
39 | UC-002: Admin Portal | User Interface | High | Check when click on the bell icon in the navbar | Event - Click | User should be redirected to the track issues page |  |  | Pass |  |  | Pass
40 | UC-002: Admin Portal | User Interface | Medium | Check if badge is visible on the bell icon at the navbar in the admin portal screen | Visual | Badge with number in it should be visible |  |  | Pass |  |  | Pass
41 | UC-003: Asset Details | User Interface | High | Check when asset details screen is displayed | Visual | In the navbar, bell icon withb notification count, logout button and sidebar hamburger button should be displayed |  |  | Pass |  |  | Pass
42 | UC-003: Asset Details | User Interface | High | Check when asset details screen is displayd | Visual | Asset details should be displayed with headers asset id, assetcategory, asset status, allocated to, team, created at, created by, modified by, modified at and action |  |  | Pass |  |  | Pass
43 | UC-003: Asset Details | User Interface | High | Check when asset details screen is displayed | Visual | Action column oif the asset detailks table should have view and update button |  |  | Pass |  |  | Pass
44 | UC-003: Asset Details | User Interface | High | Check when asset details screen si displayed | Visual | Search field should be displayed at the top right corner of the assset details table |  |  | Pass |  |  | Pass
45 | UC-003: Asset Details | User Interface | High | Checn when click on view button in the action column of asset details screen | Visual | User should be redirected to asset history screen |  |  | Pass |  |  | Pass
46 | UC-003: Asset Details | User Interface | High | Check when user clicks on the update button in the action column of asset details table | Visual | Update asset modal should be displayed |  |  | Pass |  |  | Pass
47 | UC-004: Update Asset Details | User Interface | High | Check when update asset details modal is displayed and asset status is 'Allocated | Visual | Update asset modal should have asset id, asset category, asset status field, team and allocated to field with update button |  |  | Pass |  |  | Pass
48 | UC-004: Update Asset Details | User Interface | High | Check when click outside the update asset details modal | Visual | Update asset modal should be closed |  |  | Pass |  |  | Pass
49 | UC-004: Update Asset Details | User Interface | High | Check in update asset modal if asset id and asset category are editable screen | Event - Click | Asset category and asset id should not field should not be editable |  |  | Pass |  |  | Pass
50 | UC-004: Update Asset Details | User Interface | High | Check when team dropdown field is change | Event - Click | Allocated to dropdown field options should be updated corresponding to the team selected |  |  | Pass |  |  | Pass
51 | UC-004: Update Asset Details | User Interface | High | Check when asset status is Unallocated in the asset status of the update asset modal | Visual | Team and allocated to field should not be displayed |  |  | Pass |  |  | Pass
52 | UC-004: Update Asset Details | Functional | High | Check when update button is clicked in the update asset modal and all the valid data is filled | Test Data | Swal success message should be displayed and asset detail should be updated and modal shoul close | TD06 |  | Pass |  |  | Pass
53 | UC-004: Update Asset Details | Validation | High | Check when user fills other value and do not select value from allocated to dropdown in the update asset details modal. | Test Data | Swal error message 'Please select from the options below' should be displayed | TD07 |  | Pass |  |  | Pass
54 | UC-004: Update Asset Details | Functional | High | Check when asset status is Unallocated in the asset status of the update asset modal and form is submitted with valid data | Test Data | Swal success message should be displayed and asset detail should be updated and modal shoul close | TD08 |  | Pass |  |  | Pass
55 | UC-004: Update Asset Details | Validation | High | Check when user inputs in the allocated to field in the update asset details modal | Visual | Allocated to dropdown values should be updated according to user inputs |  |  | Pass |  |  | Pass
56 | UC-005: Asset History | User Interface | High | Check when asset history screen is displayed | Visual | Asset history screen should have logout button and sidebar hamburger icon in the navbar. Asset history table should be displayed under Asset History header |  |  | Pass |  |  | Pass
57 | UC-005: Asset History | User Interface | High | Check when asset history screen is displayed | Visual | Asset history table should have asset category, asset status, team,allocated to, created by, created at, modified by and modified at headers. |  |  | Fail | BUG01 |  | Pass
58 | UC-006: Add Budget | User Interface | Medium | Check when add budget modal is displayed | Visual | Allocated Budget input field and Add budget button should be displayd in the modal. |  |  | Pass |  |  | Pass
59 | UC-006: Add Budget | User Interface | Medium | Check when click on cross sign in the add budget modal | Event - Click | Add Budget modal should be closed. |  |  | Pass |  |  | Pass
60 | UC-006: Add Budget | User Interface | Medium | Check when click outside the add budget modal | Event - Click | Add budget modal should be displayed. |  |  | Pass |  |  | Pass
61 | UC-006: Add Budget | Validation | High | Check when Allocated Budget field is empty and form is submitted | Event - Click | Error message 'Please fill this field' should be displayed |  |  | Pass |  |  | Pass
62 | UC-006: Add Budget | Validation | High | Check when alphabets are entered in the Allocated Budget input field | Test Data | User should not be able to enter alphabets in the allocated budget input field | TD09 |  | Pass |  |  | Pass
63 | UC-006: Add Budget | Validation | High | Check when digit below zero is entered in the allocated budget input field | Test Data | User should not be able to enter digit below zero in the allocated budget input field | TD10 |  | Pass |  |  | Pass
64 | UC-006: Add Budget | Validation | High | Check when user enters zero in the allocated budget form field | Test Data | User should not be able to enter zero in the allocated budget fields. | TD11 |  | Pass |  |  | Pass
65 | UC-006: Add Budget | Functional | High | Check when user enters valid input in the allocated budget field | Test Data | Budget should be added in the database and all the cards under budget data heading should be updated. | TD12 |  | Pass |  |  | Pass
66 | UC-006: Add Budget | Functional | High | Check when budget is already added for the current year and user submits filled add budget form | Visual | Swal error message 'Budget for the year already exists' should be displayed |  |  | Pass |  |  | Pass
67 | UC-007: Update Budget | User Interface | Medium | Check when update budget modal is displayed | Visual | Modal should have allocated budget inout field and a update button |  |  | Pass |  |  | Pass
68 | UC-007: Update Budget | User Interface | Medium | Check when update budget modal is displayed | Visual | Allocated Budget is prefilled with current allocated budget |  |  | Pass |  |  | Pass
69 | UC-007: Update Budget | Validation | Medium | Check when form is empty and form is submitted | Event - Click | Error message 'Please fill this field' should be displayed. |  |  | Pass |  |  | Pass
70 | UC-007: Update Budget | Validation | Medium | Check when user enters text in the allocated budget field and submits the form | Test Data | No text should be filled in the allocated budget field. | TD13 |  | Pass |  |  | Pass
71 | UC-007: Update Budget | Functional | High | Check when user fills zero in the allocated budget field and submits the form | Test Data | Swal error message 'New Budget Allocation cannot be less than current alllcation ' should be displayed. | TD14 |  | Pass |  |  | Pass
72 | UC-007: Update Budget | Functional | High | check when user fills numerical value less than the current allocated budget | Test Data | Swal error message 'New Budget Allocation cannot be less than current alllcation ' should be displayed. | TD15 |  | Pass |  |  | Pass
73 | UC-007: Update Budget | Functional | High | Check when valid input is filled and form is submitted | Test Data | Swal success message should be displayed and allocated budget, utilized budget and available budget should be updated. | TD16 |  | Pass |  |  | Pass
74 | UC-008: Register New Asset | User Interface | Medium | Check when register new asset modal is displayed | Visual | Modal should have asset category, asset status, asset vendor dropdown fields and asset price input fields. Modal should have close and register asset button |  |  | Pass |  |  | Pass
75 | UC-008: Register New Asset | User Interface | High | Check when any value is selected from the asset category dropdown | Visual | Asset vendor dropdown field values should be changed according to selected asset category |  |  | Pass |  |  | Pass
76 | UC-008: Register New Asset | User Interface | High | Check when any value is selected from the asset vendor dropdown | Visual | Asset price should be updated according to values selected in the asset vendor dropdown field |  |  | Pass |  |  | Pass
77 | UC-008: Register New Asset | User Interface | High | Check when allocated is selected in the asset status dropdown field | Visual | Team and allocated to field should be displayed in the register new asset form |  |  | Pass |  |  | Pass
78 | UC-008: Register New Asset | User Interface | High | Check when unallocated is field is selected in the asset status field | Visual | Team and allocated to field should be not displayed in the register new asset form |  |  | Pass |  |  | Pass
79 | UC-008: Register New Asset | User Interface | High | Check when allocated is selected in the asset status dropdown field, anu value is selected in the team dropdown field | Visual | Allocated To dropdown field values should be changed according to team selected in the team dropdown field. |  |  | Pass |  |  | Pass
80 | UC-008: Register New Asset | User Interface | High | Check when register new asset modal is displayed, asset price field is editable | Visual | Asset Price field should not be ediatable |  |  | Pass |  |  | Pass
81 | UC-008: Register New Asset | Validation | High | Check when empty form is submitted | Visual | Form should not be submitted |  |  | Pass |  |  | Pass
82 | UC-008: Register New Asset | Validation | High | Check when a field is empty and form is submitted | Visual | Register new asset form should not be submiited |  |  | Pass |  |  | Pass
83 | UC-008: Register New Asset | Functional | High | Check when all the valid inputs are filled and form is submitted | Visual | Swal success message ' Asste registered successfully' should be displayed and admin portal screen should be refreshed |  |  | Pass |  |  | Pass
84 | UC-008: Register New Asset | Validation | High | Check when asset price is more than available budget | Visual | Swal warning message 'Asset Prcie is more than available budget' should be displayed |  |  | Pass |  |  | Pass
85 | UC-008: Register New Asset | Validation | High | Check when in the allocated to field input is not selected from the dropdown and form is submitted | Visual | Swal error message 'Please selected from the options' should be displayed |  |  | Pass |  |  | Pass
86 | UC-009: Add User | User Interface | Medium | Check when add user screen is displayed | Visual | Add user form should be displayed with username, user email, user role , password and team fields should be displayed. Register button should be visible in the add user form. |  |  | Pass |  |  | Pass
87 | UC-009: Add User | Validation | High | Check when empty form is submitted | Visual | Add user form should not be submitted |  |  | Pass |  |  | Pass
88 | UC-009: Add User | Validation | High | Check when a field is empty and form is submitted | Visual | Error message 'Please fill this field' should be displayed. |  |  | Pass |  |  | Pass
89 | UC-009: Add User | Validation | High | Check when invalid email format is passed and form is submitted | Visual | Error message 'Please enter a valid email addressh should be displayed'. |  |  | Pass |  |  | Pass
90 | UC-009: Add User | Validation | High | Check when invalid password is passed and form is submitted | Visual | Swal error message with validation message which is failed. |  |  | Pass |  |  | Pass
91 | UC-009: Add User | Functional | High | Check when all the valid inputs are filled and form is submitted | Visual | Swal success message 'User added successfully' should be displayed and user should be redirected to admin portal screen |  |  | Fail | BUG02 |  | Pass
92 | UC-009: Add User | Validation | High | Check when no user role is selected and form is submitted | Visual | Error message 'Please fill this field' should be displayed |  |  | Pass |  |  | Pass
93 | UC-010: Add Vendor | User Interface | Medium | Check when add vendor screen is displayed | Visual | Add vendor form with asset category,vendor name , vendor email, vendor contact number, vendor address and asset price per unit fields should be displayed and register vendor should also be displayed in the form. |  |  | Pass |  |  | Pass
94 | UC-010: Add Vendor | User Interface | Medium | Check when add vendor screen is displayed | Visual | Asset category should be a dropdown field with prefilled values. |  |  | Pass |  |  | Pass
95 | UC-010: Add Vendor | Validation | Medium | Check when empty form is submitted | Visual | Form should not be submitted |  |  | Pass |  |  | Pass
96 | UC-010: Add Vendor | Validation | Medium | Check when any of the field is empty and form is submitted | Visual | Form should not be submitted and error message 'Please fill this field should be displayed |  |  | Pass |  |  | Pass
97 | UC-010: Add Vendor | Validation | Medium | Check when invalid email format is filled and form is submiited | Test Data | Form should not submitted and error message should be displayed | TD17 |  | Fail | BUG03 |  | Pass
98 | UC-010: Add Vendor | Validation | Medium | Check when invalid vendor contact number is filled and form is submitted | Test Data | Form should not be submiitted and error message should be displayed | TD18 |  | Pass |  |  | Pass
99 | UC-010: Add Vendor | Validation | Medium | Check when in the asset price per unit, text is filled and form is submitted | Test Data | Form should not be submitted and error message should be displayed | TD19 |  | Pass |  |  | Pass
100 | UC-010: Add Vendor | Validation | Medium | Check when negative integer value is filled in asset price per unit and form is submitted | Test Data | Form should not be submitted and error message should be displayed | TD20 |  | Pass |  |  | Pass
101 | UC-010: Add Vendor | Functional | High | Check when all the valid inputs are filled and form is submitted | Test Data | Swal success message should be displayed and user should be redirected to admin portal | TD21 |  | Pass |  |  | Pass
102 | UC-010: Add Vendor | User Interface | Medium | Check when add vendor screen is displayed | Visual | Add vendor screen should have a navbar with a logout button, hamburger button and bell icon with a round badge |  |  | Pass |  |  | Pass
103 | UC-010: Add Vendor | User Interface | Medium | Check when hamburger icon button is clicked | Event - Click | Sidebar should be displayed with Home, Track Issues and Add user buttons should be displayed |  |  | Pass |  |  | Pass
104 | UC-010: Add Vendor | User Interface | Medium | Check when click outside the sidebar in asset vendor screen | Visual | Sidebar should be closed |  |  | Pass |  |  | Pass
105 | UC-011: Track Issues | User Interface | Medium | Check when track issues button is clicked in the sidebar of the admin portal, add user or in the asset vendor screen | Visual | Track issues screen should be displayed |  |  | Pass |  |  | Pass
106 | UC-011: Track Issues | User Interface | Medium | Check when track isues screen is displayed | Visual | Track issues screen should have a navbar with bell icon with badge icon, logout button and sidebar hamburger button. |  |  | Pass |  |  | Pass
107 | UC-011: Track Issues | User Interface | Medium | Check when track issues is displayed | Visual | Track issues should have three cards under Total issues and count heading, four cards under pending issues header and four under new asset request. |  |  | Pass |  |  | Pass
108 | UC-011: Track Issues | User Interface | Medium | Check when click on total issues card under the sub heading Total issues and request | Visual | User should navigates to issues screen which contains all the issues . |  |  | Pass |  |  | Pass
109 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on software issues card on track issues screen | Visual | User should navigates to pending software issues screen which contains only pending software related issues. |  |  | Pass |  |  | Pass
110 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on hardware issues card on track issues screen | Visual | User should navigates to pending hardware issues screen which contains only pending hardware related issues. |  |  | Pass |  |  | Pass
111 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on replacewment issues card on track issues screen | Visual | User should navigates to pending replacewment issues screen which contains only pending replacement related issues. |  |  | Pass |  |  | Pass
112 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on damage issues card on track issues screen | Visual | User should navigates to pending damage issues screen which contains only pending damage related issues. |  |  | Pass |  |  | Pass
113 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on total pending issues card on track issues screen | Visual | User should navigates to pending issues screen which contains only pending issues |  |  | Pass |  |  | Pass
114 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on total new asset requests card on track issues screen | Visual | User should navigates to all asset requests screen which contains all new asset requests |  |  | Pass |  |  | Pass
115 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on pending new desktop asset requests card on track issues screen | Visual | User should navigates to pending desktop new asset requests screen which contains pending new desktop requests |  |  | Pass |  |  | Pass
116 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on pending new laptop asset requests card on track issues screen | Visual | User should navigates to pending laptop new asset requests screen which contains pending new laptop requests |  |  | Pass |  |  | Pass
117 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on pending new dongle asset requests card on track issues screen | Visual | User should navigates to pending dongle new asset requests screen which contains pending new dongle requests |  |  | Pass |  |  | Pass
118 | UC-011: Track Issues | User Interface | Medium | Check if user clicks on pending new mobile asset requests card on track issues screen | Visual | User should navigates to pending mobile new asset requests screen which contains pending new mobile requests |  |  | Pass |  |  | Pass
119 | UC-011: Track Issues | User Interface | Medium | Check when employee created a new issue or request a new asset | Visual | Total issues count pending issue count and the respective issue count should be updated without refreshing the page and a alert message should be displayed with message 'New request is reaised'. |  |  | Pass |  |  | Pass
120 | UC-012: Update Request or Issue Status | User Interface | Medium | Check when issue and request details screen is displayed | Visual | Request and issue screen should have logout and hamburger button in the navbar. Below navbar there should be table with a search field on top right corner of the table. |  |  | Pass |  |  | Pass
121 | UC-012: Update Request or Issue Status | User Interface | Medium | Check when issue and request details screen is displayed | Visual | The issue or request details table should have view and update button in the action column of the table |  |  | Pass |  |  | Pass
122 | UC-012: Update Request or Issue Status | User Interface | Medium | Check when issues and request details screen is displayed and view button is clicked | Event - Click | User should be redirected to the issue id or request id screen |  |  | Pass |  |  | Pass
123 | UC-012: Update Request or Issue Status | User Interface | Medium | Check when user clicks on update button in the table | Event - Click | Issue or request status update modal should be displayed with prefilled values |  |  | Pass |  |  | Pass
124 | UC-012: Update Request or Issue Status | User Interface | Medium | Check when update issue or request status modal is displayed | Visual | Check if only issue or request status dropdown is displayed |  |  | Pass |  |  | Pass
125 | UC-012: Update Request or Issue Status | User Interface | Medium | Check when issue or request status modal is displayed, editablity of the input fields | Visual | Only issue or request status dropdown field should be editable |  |  | Pass |  |  | Pass
126 | UC-012: Update Request or Issue Status | User Interface | Medium | Check when issue or request status is changed and update button is clicked | Event - Click | Swal success message should be displayed and user should be redirected to track issues screen with updated counts |  |  | Pass |  |  | Pass
127 | UC-013: Employee Portal | User Interface | Medium | Check when employee logged in | Visual | Employee Portal should be displayed with allocated assets table and asset issues table. Employee portal should have a logout button, a requwest new asset button in the nvabar |  |  | Pass |  |  | Pass
128 | UC-013: Employee Portal | User Interface | Medium | Check when click on request new asset button in the navbar | Event - Click | Request new asset modal should be displayed |  |  | Pass |  |  | Pass
129 | UC-013: Employee Portal | User Interface | Medium | Check when click on outside of the request new asset modal | Event - Click | Request new asset modal should be closed. |  |  | Pass |  |  | Pass
130 | UC-013: Employee Portal | User Interface | Medium | Check when click on report issue button on the allocated assets table | Event - Click | Report issue modal should be displayed with prefilled form |  |  | Pass |  |  | Pass
131 | UC-013: Employee Portal | User Interface | Medium | Check when click outside the report issue modal. | Event - Click | Report issue modal should be closed |  |  | Pass |  |  | Pass
132 | UC-014: Request New Asset | User Interface | Medium | Chek when request new asset modal is displayed | Visual | Request new asset modal should have asset category dropdown field and request description text fields with close and request asset buttons |  |  | Pass |  |  | Pass
133 | UC-014: Request New Asset | Validation | Medium | Check when form is empty and form is submitted | Visual | Form should not be submitted and error message 'Please fill this field should be displayed |  |  | Pass |  |  | Pass
134 | UC-014: Request New Asset | Validation | Medium | Check when requet description field is empty and form is submitted | Visual | Form should not be submitted and error message 'Please fill this field should be displayed |  |  | Pass |  |  | Pass
135 | UC-014: Request New Asset | Validation | Medium | Check when asset category is not selected from the dropdown and form is submitted | Visual | Form should not be submitted and error message 'Please fill this field should be displayed |  |  | Pass |  |  | Pass
136 | UC-014: Request New Asset | Functional | Medium | Check when all the fields are filled with valid inputs when asset status is Allocated | Test Data | Form should be submiited and success Swal message should be displayed. Asset Issues table should be updated and modal should close. | TD22 |  | Pass |  |  | Pass
137 | UC-014: Request New Asset | Functional | Medium | Check when all the fields are filled with valid inputs when asset status is Unallocated | Test Data | Form should be submiited and success Swal message should be displayed. Asset Issues table should be updated and modal should close. | TD23 |  | Fail | BUG04 |  | Pass
138 | UC-014: Request New Asset | Validation | Medium | Check when user fills the value in the allocated to field other than dropdown value from the dropdown | Test Data | Form should not be submitted and Swal error message 'Please select from options below | TD24 |  | Pass |  |  | Pass
139 | UC-015: Report Issue | User Interface | Medium | Check when report issue modal is displayed | Visual | Report modal should have asset id, asset category, issue type dropdown field and issue description text field. THe modal shoukld have close and submit button |  |  | Pass |  |  | Pass
140 | UC-015: Report Issue | User Interface | Medium | Check when report issue modal is displayed , if asset id and asset category field is editable | Event - Click | Asset id and asset category field should not be editable |  |  | Pass |  |  | Pass
141 | UC-015: Report Issue | Validation | Medium | Check when empty form is submitted | Visual | Form should not be submitted and error message should be displayed |  |  | Pass |  |  | Pass
142 | UC-015: Report Issue | Validation | Medium | Check when issue type is not selected and form is submitted | Test Data | Form should not be submitted and error message should be displayed | TD25 |  | Pass |  |  | Pass
143 | UC-015: Report Issue | Validation | Medium | Check when issue description is empty and form is submitted | Test Data | Form should not be submitted and error message should be displayed | TD26 |  | Pass |  |  | Pass
144 | UC-015: Report Issue | Functional | High | Check when valid input is filled and form is submitted | Test Data | Form should be submiited and success Swal message should be displayed. Asset Issues table should be updated and modal should close. | TD27 |  | Pass |  |  | Pass
145 | UC-016: Logout | Functional | High | Check when user clicks on exit icon | Event - Click | User should be logged out and redirected to login screen |  |  | Pass |  |  | Pass
146 | UC-017 Add Quotation | User Interface | High | Check when add quotation screen is displayed | Visual | Vendor details screen should have vendor details table with add quotation and view button in the action column if the table |  |  | Pass |  |  | Pass
147 | UC-017 Add Quotation | User Interface | High | Check when vendor details screen is displayed and quotation file of the vendor is not present | Visual | View button should not be visible when quotation of the vendor is not present already |  |  | Pass |  |  | Pass
148 | UC-017 Add Quotation | User Interface | High | Check when vendor's quotation file is already present in the add quotation screen | Visual | View button should be visible |  |  | Pass |  |  | Pass
149 | UC-017 Add Quotation | Functional | High | Check when add quotation screen is displayed | Visual | Navbar should have user name, logout button and sidebar hamburger icon |  |  | Pass |  |  | Pass
150 | UC-017 Add Quotation | Functional | High | Check when click on view buttonm | Event - Click | User should be redirected to quotation details screen |  |  | Pass |  |  | Pass
151 | UC-017 Add Quotation | Functional | High | Check when click on add quotation button in the action column of the vendor details table on thw add qutoation screen | Event - Click | Upload file/files widget should be displayed |  |  | Pass |  |  | Pass
152 | UC-017 Add Quotation | Functional | High | Check when user uploads file more than 10MB | Event - Click | Error message should be disiplayd in the upload file widget |  |  | Pass |  |  | Pass
153 | UC-017 Add Quotation | Functional | High | Check when user selects multiple files to upload in the upload file widget on the add quotation screen | Visual | All the files should be uploaded |  |  | Pass |  |  | Pass
154 | UC-018 Quotation Details | User Interface | High | Check when quotation details screen is displayed | Visual | Quotation details table should be displayed. Vendor should be displayed above the quotation details table. Navabar should include user name, logout button and hamburger sidebar icon. |  |  | Pass |  |  | Pass
155 | UC-018 Quotation Details | User Interface | High | Check when quotation details screen is displayed | Visual | Quotation details should have remove and download button for every row in the action column |  |  | Pass |  |  | Pass
156 | UC-018 Quotation Details | Functional | High | Check when click on the remove button in the action column of the quotation details table on the quotation details screen | Event - Click | The quotation should be removed from quotation details table and quotation should be removed from database. Swal success message should be displayed and quotation screen should be refershed |  |  | Pass |  |  | Pass
157 | UC-018 Quotation Details | Functional | High | Check when click on download button and quotation file format is docs on the quotation details screen | Event - Click | The quotation file should be downloaded |  |  | Pass |  |  | Pass
158 | UC-018 Quotation Details | Functional | High | Check when click on download button and quotation file format is pdf on the quotation details screen | Event - Click | The quotation file preview should be displayed and user should be able to download the file from the preview |  |  | Fail | BUG5 |  | Pass
159 | UC-017 Add Quotation | Functional | High | Check when user clicks on add quotation button and vendor already have quotaion files available in the database | Event - Click | The new quotation files should be uploaded to the cloudinary lubrary and their details should stored in the databsae with the existing files details. |  |  | Fail | BUG6 |  | Pass

## BUGS >>
BUGS Status
Sum of Bug ID | Column Labels
Row Labels | (blank) | Grand Total
(blank)
Grand Total

## Bugs
Bug ID | Bug Description | Test Result | Type of Issue | Status | Reported By | Fixed By/ Assigned To | Tester Comments | Developer Comment | Tester Comments
BUG1 | In the asset history table the values in the created at and created by column are not correct | Fail | Functionality | Pass | Abhinandan Kumar | Abhinandan Kumar
BUG2 | On register new user, user is not registered and not redirected to dashboard screen when user role is ad min | Fail | Functionality | Pass | Abhinandan Kumar | Abhinandan Kumar
BUG3 | Email is not checked and no error message is displayed for invalid email format | Fail | Functionality | Pass | Abhinandan Kumar | Abhinandan Kumar
BUG4 | When asset status is unallocated, the new asset is not registered | Fail | Functionality | Pass | Abhinandan Kumar | Abhinandan Kuamr
BUG5 | User is unable to download pdf files from the quotation details screen | Fail | Functionality | Pass | Abhinandan Kumar | Abhinandan Kumar
BUG6 | When user add new quotation files when vendor already have quotation files, new files removes previous files | Fail | Functionality | Pass | Abhinandan Kumar | Abhinandan Kumar

## Test Data >>
Test Data
Prepared By | Updated On | Verified By | Verified On

## Test Data
Use Case | Test Data ID | Test Data
UC:001 Login | TD01 | { "user_email":"", "password":"test12345" }
UC:001 Login | TD02 | { "user_email":"abc@gmail.com", "password":"" }
UC:001 Login | TD03 | { "user_email":"abc", "password":"test12345" }
UC:001 Login | TD04 | { "user_email":"abc", "password":"test" }
UC:001 Login | TD05 | { "user_email":"abc@gmail.com", "password":"test@1234" }
UC-004: Update Asset Details | TD06 | { "asset_id":13, "asset_status":"Allocated", "allocated_to":'YM5 - new, "team":"SAP", "asset_category":'Laptop' }
UC-004: Update Asset Details | TD07 | { "asset_id":14, "asset_status":"Allocated", "allocated_to":'new, "team":"SAP", "asset_category":'Dongle' }
UC-004: Update Asset Details | TD08 | { "asset_id":04, "asset_status":"Unallocated", "allocated_to":'YM5 - new, "team":"SAP", "asset_category":'Dongle' }
UC-006: Add Budget | TD09 | { "allocated_budget":"asasas" }
UC-006: Add Budget | TD10 | { "allocated_budget":-1200000 }
UC-006: Add Budget | TD11 | { "allocated_budget":0 }
UC-006: Add Budget | TD12 | { "allocated_budget":500000 }
UC-007: Update Budget | TD13 | { "allocated_budget":"asasas" }
UC-007: Update Budget | TD14 | { "allocated_budget":0 }
UC-007: Update Budget | TD15 | { "allocated_budget":40000 }
UC-007: Update Budget | TD16 | { "allocated_budget":60000 }
UC-010: Add Vendor | TD17 | { "asset_category":"Laptop", "vendorName":"werwer", "vendorEmail":"asas", "vendorContactNumber":1234567899, "vendoraddress":"asdasd", "pricePerUnit":2500 }
UC-010: Add Vendor | TD18 | { "asset_category":"Dongle", "vendorName":"abcdr", "vendorEmail":"abcdr@gmail.com", "vendorContactNumber":12345678, "vendoraddress":"asdasd", "pricePerUnit":2500 }
UC-010: Add Vendor | TD19 | { "asset_category":"Mobile", "vendorName":"abr", "vendorEmail":"abr@gmail.com", "vendorContactNumber":12345678, "vendoraddress":"asdasd", "pricePerUnit":"asacs" }
UC-010: Add Vendor | TD20 | { "asset_category":"Desktop", "vendorName":"abcdrt", "vendorEmail":"abcdrt@gmail.com", "vendorContactNumber":12345678, "vendoraddress":"asdasd", "pricePerUnit":-12112 }
UC-010: Add Vendor | TD21 | { "asset_category":"Desktop", "vendorName":"abcdrt", "vendorEmail":"abcdrt@gmail.com", "vendorContactNumber":12345678, "vendoraddress":"asdasd", "pricePerUnit":12112 }
UC-014: Request New Asset | TD22 | { "asset_category":"Laptop", "asset_status":"Allocated", "asset_vendor":"asas", "asset_price":1234567899, "team":"asdasd", "allocated_to":"YM5 - new" }
UC-014: Request New Asset | TD23 | { "asset_category":"Laptop", "asset_status":"Unallocated", "asset_vendor":"asas", "asset_price":1234567899, }
UC-014: Request New Asset | TD24 | { "asset_category":"Laptop", "asset_status":"Allocated", "asset_vendor":"asas", "asset_price":1234567899, "team":"asdasd", "allocated_to":"YM5 - new" }
UC-015: Report Issue | TD25 | { "asset_category":"Laptop", "assetID":104, "issue_type":"", "issue_description":"sdasda" }
UC-015: Report Issue | TD26 | { "asset_category":"Laptop", "assetID":104, "issue_type":"Software", "issue_description":"" }
UC-015: Report Issue | TD27 | { "asset_category":"Laptop", "assetID":104, "issue_type":"Software", "issue_description":"sdasda" }